## Product Backlog
Product Backlog
|  | User Story | [7 empty] | https://asana.com/resources/story-points
User Story ID | Use Case | As a/an... | I want to... | so that... | Sprint | Priority | Story Status | Category | Task | Estimated Size | Notes
1001 | Manage Attribute | Adminstrator | create an new attribute | customer can access the new attribute. | Sprint 1 | Medium | In Progress | Admin; Attribute | Create button to Add Attribute | 1
1002 | Manage Attribute | Adminstrator | update the attribute detail | customer can acccess the updated attribute. | Sprint 1 | Medium | In Progress | Admin; Attribute | Create Attribute Form | 3 | - Name must be unique Fields for Attribute Detail: - name - active indicator
1003 | Manage Attribute | Adminstrator | delete an attribute | customer no longer accesses the non-applicable attribute. | Sprint 1 | Medium | In Progress | Admin; Attribute | Create button to delete Attribute | 1
1004 | Manage Brand | Adminstrator | create a new brand | customer can access the new brand. | Sprint 1 | Medium | Cancelled | Admin; Brand | Create button to Add Brand | 1 | No longer need Brand
1005 | Manage Brand | Adminstrator | update the brand detail | customer can acccess the updated brand. | Sprint 1 | Medium | Cancelled | Admin; Brand | Create Brand Form | 3 | Fields for Brand: - name - active indicator - Name must be unique - Default Active Indicator to uncheck
1006 | Manage Brand | Adminstrator | delete a brand | customer no longer accesses the non-applicable brand. | Sprint 1 | Medium | Cancelled | Admin; Brand | Create button to delete Brand | 1
1007 | Manage Product | Adminstrator | create a new product | customer can access the new product. | Sprint 1 | Medium |  | Admin; Product | Create button to Add Product | 1
1008 | Manage Product | Adminstrator | modify the product information | customer can acccess the updated product information. | Sprint 1 | Medium |  | Admin; Product | Create Product Form | 3 | Fields for Product Detail: - name - description - digital indicator - active indicator - attribute - sku Comments: - Name must be unique - Default Active Indicator to uncheck - Default Digital Indicatory to check
1009 | Manage Product | Adminstrator | delete a product | customer no longer accesses the non-applicable product. | Sprint 1 | Medium |  | Admin; Product | Create button to delete Product | 1
1010 | Access Attribute | Customer that distributes the product | fetch a product information | I can update our distributing site with the most recent data. | Sprint 1 | Medium |  | Customer; Product | Create UI for user to search Product, Create display for data | 3

## Acceptance Criteria
User Story id: 1001
As an administrator I want to create an new attribute So that customer can access the new attribute.
Acceptance Criteria
Scenario 1: Given I am an administrator When I select the option to Add Attribute Then the system successfully displays a blank Attribute form. | Example 1 using Given, When, Then statement
Acceptance Criteria 1: User sees the option to Add Attribute Acceptance Criteria 2: When user clicks Add Attribute, user sees a blank Attribute form | Example 2 using checklist format
User Story id: 1002
As an administrator I want to modify the attribute detail: - name - active indicator So that customer can acccess the updated attribute.
Acceptance Criteria
Scenario 1 (Happy Path): Given I am an administrator and I am on a blank or existing Attribute form When I edit the name and/or active indicator and I click Save Then the system verifies the Attribute name is unique, if the Attribute name is unique then the system saves the new data, and then the system displays a successful message: "Your data has been saved successfully." Scenario 2 (Alternate Path): Given I am an administrator and I am on a blank or existing Attribute form When I edit the name and/or active indicator and I click Save Then the system verifies the Attribute name is unique, if the Attribute name is not unique then the system displays an error message: "Attribute name already existed. Please change the Attribute name to be unique." and then the use case ends (does nothing). | Example 1 using Given, When, Then statement
Acceptance Criteria 1: User is able to edit the Active Indicator and Name fields Acceptance Criteria 2: System verifies the Attribute name is unique across the database. Acceptance Criteria 3: If Attribute name is not unique, do not allow system to save. Display error message to user. Acceptance Criteria 4: If Attribute name is unique, allow system to save. Display successful mssage to user. | Example 2 using checklist format
User Story id: 1003
As an administrator I want to delete an attribute So that customer no longer accesses the non-applicable attribute.
Acceptance Criteria
Scenario 1: Given I am an administrator and I am on an Attribute form When I click Delete Then the system prompts a confirmation message: "Are you sure you want to delete this Attribute? This Attribute will no longer exists in the system." When I respond Yes Then the system deletes the Attribute and sets the related Product's Attribute to NULL. Scenario 2: Given I am an administrator and I am on an Attribute form When I click Delete Then the system prompts a confirmation message: "Are you sure you want to delete this Attribute? This Attribute will no longer exists in the system." When I respond No Then the use case ends. | Example 1 using Given, When, Then statement
Acceptance Criteria 1: User sees the option to Delete Acceptance Criteria 2: When user clicks Delete, the system prompts a confirmation message: "Are you sure you want to delete this Attribute? Deleting this Attribute will be unrecoverable." Acceptance Criteria 3: User sees an option to select Yes or No. Acceptance Criteria 4: If user selects "Yes" for the delete confirmation message, then the system deletes the Attribute Data and set all related Product's Attribute to NULL. Acceptance Criteria 5: If user selects "No" for the delete confirmation message, then the use case ends. | Example 2 using checklist format
User Story id: 1010
As a customer that distributes the product I want to fetch a product information So that I can update our distributing site with the most recent data.
Acceptance Criteria
Scenario 1: Given I am a customer When I search the product by the product name Then the system searches for all product name containing those entered value and successfully displays all of the matched product(s) detail. (Note: allow customer to search by partial match on product name) Scenario 2: Given I am a customer When I search the product by the product sku Then the system searches for all product sku containing those entered value and successfully displays all of the matched product(s) detail. (Note: allow customer to search by partial match on product sku)
Acceptance Criteria 1: User sees the option to search for product information by name or sku Acceptance Criteria 2: When user searches by product name, then the system searches for all products containing those values, and then displays all of the matched product(s) detail. Acceptance Criteria 3: When user searches by product sku, then the system searches for all products containing those values, and then displays all of the matched product(s) detail.